## Online_CV_GN
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
Apr 4, 2017 | Initial commit | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-04-04T09:00:00+05:30","ped":"2017-04-10T00:00:00+05:30"}) |  | 2017-05-09 17:00 |  | Completed | 1 | https://trello.com/c/o1BPzzVx
Apr 4, 2017 | Update Readme.md | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-04-05T09:00:00+05:30","ped":"2017-04-12T18:00:00+05:30"}) |  |  |  | Completed | 2 | https://trello.com/c/zIbHxGds
Apr 4, 2017 | Initial ER diagram | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-04-05T09:00:00+05:30","ped":"2017-04-11T18:00:00+05:30"}) |  |  |  | Completed | 3 | https://trello.com/c/uJTdAvyV
Apr 5, 2017 | Add files via upload | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-04-05T15:00:00+05:30","ped":"2017-04-12T18:00:00+05:30"}) |  |  |  | Completed | 4 | https://trello.com/c/CeXvJHXs
Apr 5, 2017 | Initial Project creation | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-04-05T15:00:00+05:30","ped":"2017-04-13T09:00:00+05:30"}) |  |  |  | Completed | 5 | https://trello.com/c/Lg6zqBWu
Apr 6, 2017 | Created home page | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-04-07T09:00:00+05:30","ped":"2017-04-14T18:00:00+05:30"}) |  |  |  | Completed | 6 | https://trello.com/c/f2hZE9Tu
Apr 7, 2017 | Commit changes see below | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-04-07T09:00:00+05:30","ped":"2017-04-17T09:00:00+05:30"}) |  |  |  | Completed | 7 | https://trello.com/c/WCyCV3sD
Apr 9, 2017 | Insertion part for the User Registration | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-04-09T09:00:00+05:30","ped":"2017-04-22T00:00:00+05:30"}) |  |  |  | Completed | 13 | https://trello.com/c/Kdpi4afZ
Apr 9, 2017 | Validation for the User Registration - Attached Libraries for JQuery | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-04-10T10:00:00+05:30","ped":"2017-05-01T00:00:00+05:30"}) |  |  |  | Completed | 12 | https://trello.com/c/LAi4GFCo
Apr 9, 2017 | Merge remote-tracking branch 'origin/master' | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-04-09T10:00:00+05:30","ped":"2017-04-24T09:00:00+05:30"}) |  |  |  |  | 11 | https://trello.com/c/OvhE9unp
Apr 9, 2017 | Validation for the User Registration | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-04-09T10:00:00+05:30","ped":"2017-04-21T09:00:00+05:30"}) |  |  |  |  | 10 | https://trello.com/c/AJlGp2Up
Apr 9, 2017 | Update ER with User tables | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-04-09T10:00:00+05:30","ped":"2017-04-18T18:00:00+05:30"}) |  |  |  |  | 9 | https://trello.com/c/3232wnEB
Apr 9, 2017 | initial DB backup | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-04-09T09:00:00+05:30","ped":"2017-04-16T00:00:00+05:30"}) |  |  |  |  | 8 | https://trello.com/c/cHQMDQMn
Apr 12, 2017 | Insertion part for the User Registration | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-04-12T10:00:00+05:30","ped":"2017-04-25T00:00:00+05:30"}) |  |  |  | Completed | 23 | https://trello.com/c/raOMyPeH
Apr 12, 2017 | Added username & password fields, modify validations | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-04-12T09:00:00+05:30","ped":"2017-04-30T00:00:00+05:30"}) |  |  |  | Completed | 22 | https://trello.com/c/WpyKGeqw
Apr 12, 2017 | Implement search user query from username | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-04-12T09:00:00+05:30","ped":"2017-04-27T09:00:00+05:30"}) |  |  |  |  | 21 | https://trello.com/c/6pnWEN7o
Apr 12, 2017 | Update DB password | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-04-12T09:00:00+05:30","ped":"2017-04-19T18:00:00+05:30"}) |  |  |  |  | 20 | https://trello.com/c/gatjPbnJ
Apr 12, 2017 | Create: Implement search queries and insert queries to DB | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-04-12T09:00:00+05:30","ped":"2017-05-01T09:00:00+05:30"}) |  |  |  |  | 19 | https://trello.com/c/W6N2CZXi
Apr 12, 2017 | Update: to retrieve params from registerUser & save them to DB | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-04-12T09:00:00+05:30","ped":"2017-05-02T09:00:00+05:30"}) |  |  |  |  | 18 | https://trello.com/c/mqsEHsFP
Apr 12, 2017 | Merge remote-tracking branch 'refs/remotes/origin/master' into My_Branch | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-04-12T09:00:00+05:30","ped":"2017-05-06T00:00:00+05:30"}) |  |  |  |  | 14 | https://trello.com/c/Y3G1uwIC
Apr 12, 2017 | HEAD changes | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-04-12T09:00:00+05:30","ped":"2017-04-18T00:00:00+05:30"}) |  |  |  |  | 15 | https://trello.com/c/I55DQVAV
Apr 12, 2017 | Synchronized with ER changes, Added sample records | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-04-12T08:00:00+05:30","ped":"2017-04-30T00:00:00+05:30"}) |  |  |  |  | 17 | https://trello.com/c/GhgibrS4
Apr 12, 2017 | Update BIT datatype to BOOLEAN | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-04-12T08:00:00+05:30","ped":"2017-04-24T09:00:00+05:30"}) |  |  |  |  | 16 | https://trello.com/c/I9bCmqLy
Apr 13, 2017 | Merge pull request #4 from ganithDev/My_Branch | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-04-13T10:00:00+05:30","ped":"2017-04-30T00:00:00+05:30"}) |  |  |  | Completed | 24 | https://trello.com/c/woeNtDwd
Apr 13, 2017 | Merge branch 'master' of https://github.com/ganithDev/myJobsSQE | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-04-13T10:00:00+05:30","ped":"2017-05-04T18:00:00+05:30"}) |  |  |  | Completed | 25 | https://trello.com/c/jkNW1OFe
Apr 13, 2017 | ER changes | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-04-13T10:00:00+05:30","ped":"2017-04-18T09:00:00+05:30"}) |  |  |  | Completed | 26 | https://trello.com/c/vSEVGNn4
Apr 15, 2017 | Database Insertion for JUnit Testing | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-04-15T10:00:00+05:30","ped":"2017-04-27T00:00:00+05:30"}) |  |  |  | Completed | 27 | https://trello.com/c/ZDtTnhZI
Apr 15, 2017 | Insertion part for the User Registration | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-04-15T10:00:00+05:30","ped":"2017-04-28T09:00:00+05:30"}) |  |  |  | Completed | 29 | https://trello.com/c/pTuQTp6m
Apr 15, 2017 | Insertion part for the User Registration | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-04-15T10:00:00+05:30","ped":"2017-04-27T18:00:00+05:30"}) |  |  |  | Completed | 28 | https://trello.com/c/Os8WCZOB
May 1, 2017 | Initial Documentation | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-05-01T09:00:00+05:30","ped":"2017-05-08T18:00:00+05:30"}) |  |  |  |  | 30 | https://trello.com/c/9QFJHHSW
May 1, 2017 | Initiate Documentation | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-05-01T09:00:00+05:30","ped":"2017-05-09T09:00:00+05:30"}) |  |  |  |  | 31 | https://trello.com/c/eZ8E9FXE
May 1, 2017 | Modify the ENUM data columns into DB Tables | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-05-01T09:00:00+05:30","ped":"2017-05-16T18:00:00+05:30"}) |  |  |  | Completed | 32 | https://trello.com/c/22wmk8w7
May 1, 2017 | SQA Plan Documentation started | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-05-02T09:00:00+05:30","ped":"2017-05-13T00:00:00+05:30"}) |  |  |  | Started,Completed | 35 | https://trello.com/c/CPiaYelO
May 2, 2017 | SQA Plan Documentation | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-05-01T09:00:00+05:30","ped":"2017-05-10T09:00:00+05:30"}) |  |  |  |  | 33 | https://trello.com/c/IvYYjaKI
03-05-2017 | Created Unit Test Classes | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-05-01T09:00:00+05:30","ped":"2017-05-10T09:00:00+05:30"}) |  |  |  | Completed | 34 | https://trello.com/c/4rrYv34j
03-05-2017 | Tried to install Bugzilla for Windows | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-05-05T09:00:00+05:30","ped":"2017-05-16T18:00:00+05:30","esd":"2017-05-05T00:07:12+05:30","eed":"2017-05-05T00:09:48+05:30"}) |  |  |  | Started,Completed | 38 | https://trello.com/c/oX9FOtIZ
04-05-2017 | Do the SQA Plan Documentation | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-05-04T09:00:00+05:30","ped":"2017-05-15T09:00:00+05:30"}) |  |  |  | processing,Completed | 36 | https://trello.com/c/PlwHhQr3
04-05-2017 | Installed Bugzilla for Windows | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-05-01T09:00:00+05:30","ped":"2017-05-11T18:00:00+05:30"}) |  |  |  | Completed | 37 | https://trello.com/c/AumY3KIg
05-05-2017 | SQA Plan Documentation Finished | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-05-01T09:00:00+05:30","ped":"2017-05-13T00:00:00+05:30"}) |  |  |  | Completed | 39 | https://trello.com/c/WO3Cxhzh
05-05-2017 | Add bugs to the Bugzilla and fixed it | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-05-01T09:00:00+05:30","ped":"2017-05-13T00:00:00+05:30"}) |  |  |  | Completed | 40 | https://trello.com/c/c4QQIWcQ
05-05-2017 | Redesign the Registration process with Hibernate database integration. | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-05-06T18:00:00+05:30","ped":"2017-05-28T00:00:00+05:30"}) |  |  |  | Completed | 42 | https://trello.com/c/Mgx8q8VK
06-05-2017 | Started SQA Requirement Documentation | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-05-05T18:00:00+05:30","ped":"2017-05-19T00:00:00+05:30"}) |  |  |  | Started,Completed | 41 | https://trello.com/c/7L2QhxxO
06-05-2017 | Log #5 and #7 bugs, Started Designing , Create and Upload DB backup, Review Documents | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-05-06T12:30:00+05:30","ped":"2017-05-28T00:00:00+05:30","esd":"2017-05-07T10:28:00+05:30","eed":"2017-05-09T07:34:00+05:30"}) |  |  |  | Completed | 43 | https://trello.com/c/9oxdcMBz
07-05-2017 | Finished the SQA Requirement Documentation | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-05-07T09:30:00+05:30","ped":"2017-05-23T00:00:00+05:30"}) |  |  |  | Completed | 44 | https://trello.com/c/ZCZAj7MX
08-05-2017 | Start to draw UML Diagram for the Design Document | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-05-08T09:00:00+05:30","ped":"2017-05-25T09:00:00+05:30"}) |  |  |  | Started,Completed | 45 | https://trello.com/c/CQ7pSbub
09-05-2017 | Start to write Software Design Document | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-05-08T09:00:00+05:30","ped":"2017-05-21T00:00:00+05:30"}) |  |  |  | Started,Completed | 46 | https://trello.com/c/6pqkHwpu
09-05-2017 | Generate Class Diagram | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-05-11T06:00:00+05:30","ped":"2017-05-20T00:00:00+05:30"}) |  |  |  | Started,Completed | 47 | https://trello.com/c/ezaAjDFQ
09-05-2017 | Create UML Diagram | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-05-08T09:00:00+05:30","ped":"2017-05-15T18:00:00+05:30"}) |  |  |  | Started,Completed | 48 | https://trello.com/c/HNPUup30
09-05-2017 | Test the System | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-05-08T09:00:00+05:30","ped":"2017-05-14T00:00:00+05:30"}) |  |  |  | Completed | 49 | https://trello.com/c/REhDRg0X
10-05-2017 | Implement the System | --- [Elegantt data. What's this?](http://bit.ly/elegantt-for-trello-whats-this) [](Elegantt_data:dont_delete{"ignored":false,"autoPlanned":false,"ownerId":false,"dependencies":[],"psd":"2017-05-08T09:00:00+05:30","ped":"2017-05-16T09:00:00+05:30"}) |  |  |  | Completed | 50 | https://trello.com/c/GZoxyXrn

## Archived Online_CV_GN
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL